## Active Issues
Sr No | Issue Type | Issue key | What is the issue? | Priority | Status | Category | Data or Functional or Technical? | Who is fixing? | What is the Workaround?
1 | Bug | TSI-2652 | When a new firm is added and deleted in a quick succession then if the delete action is passed before the complete creation of the form then the form is added in the locator but it is not deleted from the locator. | Major | Open/In Analysis | Inconsistent Syncing | Data Level | SurePrep | User has to manually delete from the Locator or Use the traditional export feature.
2 | Bug | TSI-2671 | When the value in the 1099-R entity's Gross Distribution field is entered into the binder, the value synced in Tax Software is doubled. (For instance, if we type 2000, it will sync as 4000.) (Issue exists only on Production) | Critical | Open/In Analysis | Inconsistent Syncing | Data Level | SurePrep | Use the traditional export feature.
3 | Bug | TSI-3108 | TY-2023 - When we add a new row (with two fields entered out of five present fields) to the Farm income -'QUALIFIED BUS Inc. Ded' MIFG, which already contains the proforma data, the two entered fields are live synced as expected, but the blank fields are populated with the proforma data in the new added row. | Major | Open/In Analysis | Data Syncing | Data Level | GST | User has to manually add in the Locator or Use the traditional export feature.
4 | Bug | BIN-3327 | TY 2023 - Stage - Live Sync went on hold, and when the binder was reopened, the status change was delayed, despite the fact that the values were already reflected in the locator. Once the status changed, it changed several times. | Major | Fixed on Lower Environment | Not Reproducible | Functional | SurePrep | User needs to reopen the binder.
5 | Bug | TSI-3334 | TY-2023 On Live: Itemized Deductions>> Contributions>> Section B Donated Property>> Part IV Certification of Appraiser section “Identifying Number” field is not getting synced in Tax Software. | Major | Fixed on Lower Environment | Data Syncing | Data Level | SurePrep | User has to manually add in the Locator or Use the traditional export feature.
6 | Bug | BIN-3250 | Inconsistent issue-Live environment: Enabling of live sync is not working properly. | Critical | Open/In Analysis | Not Reproducible | Functional | SurePrep | User has to reopen the binder.
7 | Bug | TSI-3147 | TY-2023: If we have SI open reference fields in MI form & we perform Move To (Append) operation on it, after Move To (Append) operation, data is successfully added to the Target form open reference field in SPBinder but not in Tax Software via Live Sync | Major | Fixed on Lower Environment | Move To | Data Level | SurePrep | User has to manually add in the Locator or Use the traditional export feature.
8 | Bug | TSI-3116 | TY-2023:After Move To (Switch), data is switched from Source to Target form. SSN or EIN field that was present in Target form but not in Source, is switched in binder, but SSN/EIN that was present in Target form is not deleted from Locator via Live Sync. | Major | Fixed on Lower Environment | Move To | Data Level | SurePrep | User has to manually delete in the Locator or Use the traditional export feature.
9 | Bug | TSI-3228 | TY: 2023- After Move To (Switch) Source form to Target form, most of the field's data was not moved (Switched) Between Source & Target form in the Tax Software via Live Sync. | Minor | Open/In Analysis | Move To | Data Level | SurePrep | User has to manually add in the Locator or Use the traditional export feature.
10 | Bug | TSI-2889 | When the amounts are entered in Form 1095-A - Medicare premium fieldgroup for Oct/Nov/Dec fields, the fieldgroup in the binder is shifted to the blank fieldgroups which are present at the top in the sequence i.e. Jan, Feb, March when user moved from this form to another form in the Binder. Due to the existing fieldgroup behavior, when the entries are synced via Live Sync also followed the same sequence of binder i.e. Jan, Feb, March. | Minor | Open/In Analysis | Non Live Sync Issue | Data Level | SurePrep | No workaround identified.
11 | Bug | BIN-3312 | TY 2023: On disabling the Live Sync from the binder, the Import TR banner text disappears but the blank banners stays as is in the binder. | Minor | Open/In Analysis | Banner Display Issue | Functional | SurePrep | Close the banner and it will disappear.
12 | Bug | BIN-2003 | When a user executes Recalculate or Force calculate in the Leads tab, it does not display that the process has begun for 50% of the total time taken in the entire process. Furthermore, the overall time required to import data into the binder via Live Sync is long. | Minor | Open/In Analysis | Performance Issue | Performance | SurePrep | No Workaround. User has to wait until the whole process is completed.
13 | Bug | BIN-2093 | After completing the reload process in the binder and enabling Live Sync, there is a delay of 15-20 seconds before the Blue banner, Found New Information Import TR banner, and Compare TR button appear in the binder. | Minor | Open/In Analysis | Performance Issue | Performance | SurePrep | No Workaround. User has to wait for 15 to 20 secs afer reload process is completed to get the Blue banner on screen.

## Special Behaviors
Sr No | Form/Field/Fieldgroup | What situation may occur? | Steps to be taken to complete Live Sync
1 | Fieldgroup | 1. Farm Income >> 'Income accrual' - Combine other income 2. Farm Income >> 'Combined Other Income' 3. Farm Income >> Income & Expenses->'Combined other income' | The "Amount" field is required to get the "Description" field to appear in the locator after Live Sync.
2 | Field | 1099-R -Gross Distribution Field | Tax Year 2022: The PAYER'S Federal I.D. number field is mandatory to Live Sync the Gross Distribution. Tax Year 2023: The PAYER'S Federal I.D. number field is not mandatory to Live sync the Gross Distribution.
3 | Field | Rent & Royalty - 'Activity Information' - Address ( US and Foreign Address) | Tax Year 2022: All the address fields are mandatory to sync in the locator via Live Sync. Tax Year 2023: All the address fields are not mandatory to sync in the locator via Live Sync.
4 | Field | Wages>>EIN | Once EIN field is entered in the binder and synced/exported to tax software, deleting forms and fields will not delete them in the locator via Live Sync.
5 | Form/Field/Fieldgroup | When the binder goes on Hold due to any reason other that Authentication issue | When the binder goes on hold, if the authentication banner is not displayed, then re-open the binder first to sync the pending entries in the locator. If the syncing fails after re-opening binder then use the Export To Tax option.
6 | Form/Field/Fieldgroup | On opening of the binder, if the status changes from Live Sync Ready >> Live Sync In Progress >> Live Sync Active, even if there are no entries made in the binder or no pending entries from the last session. | Continue working in the binder; Live Sync will not be affected.
7 | Form/Field/Fieldgroup | The status displayed in the binder may keep on changing continuosly from Live Sync In Progress >> Live Sync Active | Continue working in the binder; Live Sync will not be affected.
8 | Field | Radio buttons, checkbox, dropdown options selected in the binder may not visually display the synced data in the browser UI after syncing in the locator. | Refresh the locator if any of the radio buttons, checkboxes, or dropdown field is not displayed in the locator. If the data doesn't appear in your browswer window, please refresh the browser window to see the updates. This is a UI issue only; calculations will not be affected.